## Sprint Plan
Date | Task | Description | Owner | Priority | Deliverable | Status
March 16, 2026 | Project Setup | Create GitHub repo, folders, README | Jeniya | High | Structured GitHub repository with README | Completed
March 16, 2027 | Design Documents | Create workflow & use case diagrams | Team | High | 2 design documents in /docs folder | Completed
March 16, 2028 | Backend Development | Build Flask app & API endpoints | Elijah | High | Working backend routes (/expenses, /prediction) | Completed
March 17, 2026 | Data Setup | Create and format sample expense dataset | Damone | Medium | CSV dataset for testing and analysis | Completed
March 17, 2026 | AI Logic | Implement spending prediction and alert system | Malachi | High | Prediction feature with alert output | Completed
March 17, 2026 | Frontend UI | Create simple interface for displaying data | Austin | Medium | Basic UI displaying expenses and predictions | Completed
March 17, 2026 | Testing | Test application functionality and fix errors | Ezekiel | High | Verified working application and endpoints | Completed
March 17, 2026 | Presentation Prep | Create slides & demo script | Jeniya | High | Completed presentation slides and demo flow | In Progress
March 18, 2026 | Final Review | Run full demo and finalize submission | Team | High | Final tested project and submission ready | Pending